| RPL |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Reliance Petroleum Limited Jamnagar Refinery Complex Project Procedure 22960-G69-000-800/1210 MOVEMENT OF ODD DIMENSION CONSIGNMENT |  |  |  |  |  |
| 01 | 15.04.98 | Issued for implementation | CD | HSP |  |
| 00 | 06.03.98 | For review by concerned department | CD | HSP |  |
| Rev | Date | Revision | By | Chkd | Appr |

# Contents

1. Purpose

2. Scope

3. Definition

4. References

5. Responsibilities

5.1 Department of Heavy Lift

5.2 Chief of Security

6. Requirement

6.1 For Small ODC’s :

6.2 For Super Heavy ODC’s

7. ODC Movement Team :

8. Equipment required for ODC movement :

9. Alternate Route for  SH - 25 Traffic -

10. Attachment											  5

# Purpose

The purpose of this procedure is to give guidelines for smooth and safe movement of Odd Dimension Consignment ( ODC ) from Reliance Jetty, Sikka to Refinery Site.

# Scope

The procedure shall cover the preparations e.g. time, route, diversions etc.  and liaison with local police / related departments.

# Definition

ODC means Odd Dimension Consignment.

# References

Letter dated 13. 01. 98, signed by Sh V Sridhar on Heavy Lifts At Jamnagar Refinery Complex.

# Responsibilities

## Department of Heavy Lift

The Department of Heavy Lift ( ODC Coordinators ) is responsible for shifting of ODCs from Jetty to its destination. Central Roadlines Corporation ( CRC ) has the contract to carry the ODC.

## Chief of Security

The Chief of  Security has the overall responsibility for security of  the consignment and ensure the smooth traffic movement during transfer of ODC and to liaise with the police for help.

# Requirement

The  procedure has been divided into two sub heads; Small ODCs and Super Heavy ODCs. This has been done to facilitate better understanding and preparation.

ODCs coming by ships are received at Reliance Jetty, Sikka. Once they are brought onshore the consignment is guarded by MTF Security.  Whenever it is required to be moved from Sikka Jetty to Refinery site advance intimation is given to Security Executive in MTF Area / Security Control Room in Refinery. Throughout  the movement of ODC, Security Control Room is kept informed.

## For Small ODC’s :

- Security Executive of Traffic Team / MTF  coordinate the movement with Sh Deepak Gupta /  Sh Sameer Gupta.

- For small ODC’s, which can be moved on single trailer - the Haul  Road is cleared and the ODC is escorted by MTF Security Executive along with MTF Patrol.

- On SH 25 the traffic is controlled by the Traffic Officer for smooth crossing of ODC from Haul Road -  SH 25 Moti Khavadi Railway Crossing - Ave J.

- Once the ODC enters Ave J, it is escorted to its destination in the Refinery by Traffic Team Officer.

## For Super Heavy ODC’s

- Information of ODC movement  is received 24 hrs in advance, from ODC Co-ordinators. Chief of Security is informed by Control Room.

- Co-ordination is done with Sh Deepak Gupta / Sh Sameer Gupta for the time, route of movement, destination and size of ODC. Time chosen for crossing the ODC on SH 25 is decided i.e. 0530 hrs or 1330 hrs, when traffic density on SH 25 is minimum.

- Police ( Panchkoshi B Div ) is requested in advance, to help control / stop the traffic on SH 25, for crossing of ODC into Ave J.

- On the day of ODC movement - Traffic team is briefed and road diversions are marked along the route. Security persons  are placed to control the diversions.

- For movement of  ODC from Jetty to Haul Road - SH 25 junction  ODC is escorted by the Security Executives of Traffic Team. The MTF Security  Team co-ordinates the movement between Jetty and MTF.

- Security Executive and his traffic team with the help of local police, stops the traffic on SH 25,  at the given time from both the sides to keep the Road clear for ODC. Once the ODC enters Ave J, SH 25 is opened for normal traffic.

- Traffic Team Officer escorts the ODC to its Destination.

# ODC Movement Team :

- Department Of Heavy Lift - ODC Coordinators.

- RPL Traffic team officer.

- Security Executive from MTF.

- Safety Officer.

# Equipment required for ODC movement :

- Route diversion boards & Safety Cones.

- Hydra with Slings to remove the portable barriers and angles.

- Road Blockage equipment.

- PA Equipment.

# Alternate Route for SH - 25 Traffic -

The alternate route has been already been planned - in case of emergency if  SH - 25 is blocked due to breakdown of trailer carrying ODC.

The route is approx. 2 KM bye passing Moti Khavadi village as per the sketch attached.

# Attachment

Alternate Route