## Sheet1
Sl.No. | Activity | Duration | Start Date | Completion Date | Responsibility
A. TURNSTILES
Objective: To procure a few full-height turnstiles locally to meet short term needs
A.1 | Finalise numbers and location |  | 1999-09-04 | 1999-09-04 | CD
A.2 | Prepare Specifications and Requisition |  | 1999-09-06 | 1999-09-06 | RL/HHP
A.3 | Techno-Commercial discussions with vendors |  | 1999-09-07 | 1999-09-07 | ALL
A.4 | LOI |  |  | 1999-09-08 | AKC
A.5 | Electrical provisions at locations |  |  | 1999-10-19 | Electrical
A.6 | Civil work including provision for overhead cover, paving, foundation, etc. |  |  | 1999-10-19 | Construction
A.7 | Expected date of Equipment availability for installation | 8 weeks |  | 1999-11-02 | Vendor
B. GATE ACTUATORS / BARRIERS
B.1 | Finalise Layout drawings |  |  | 1999-09-17 | SS
B.2 | Issue Tech. Specifications and Requisition covering following scope Supply of Gate Actuators Supply Barriers Structural Design Fabrication Specs and finish Installation supervision Spares |  |  | 1999-09-09 | RL/HHP
B.3 | Receive final quotes |  | 1999-09-15 | 1999-09-17 | AKC
B.4 | Techno-commercial discussions and finalisation of vendor (Vendors to come with Structural Design Drawings) |  | 1999-09-20 | 1999-09-25 | ALL
B.5 | Review and Approve Gate drawings / designs |  |  | 1999-09-27 | KSS/RL
B.6 | LOI |  |  | 1999-09-28 | AKC
B.7 | Electrical provisions at locations |  |  | 1999-11-02 | Electrical
B.8 | Expected date of Equipment availability for installation | 8 weeks |  | 1999-11-23 | Vendor
C. GATE FABRICATION
C.1 | Short-list 3 vendors for fabrication, galvanisation, painting and erection of gates |  |  | 1999-09-11 | AKC
C.2 | Techno-commercial discussions with vendors. |  |  | 1999-09-25 | ALL
C.3 | Prepare Order specifications and handover selected drawings / designs of the gates |  |  | 1999-09-28 | RL/HHP
C.4 | Order placement Order to include- Design dwgs., Fabrication specs +finish + tolerances specified by the actuator vendor |  |  | 1999-09-30 | AKC
C.5 | Civil works as per requirements at Gate locations |  |  | 1999-11-18 | Construction
C.6 | Expected date of Equipment availability for installation | 8-10 weeks | 1999-11-25 | 1999-12-09 | Vendor
D. ACCESS CONTROL SYSTEM
D.1 | Finalise locations (incl. Marking on dwgs.) and peak traffic |  |  | 1999-09-11 | CD/RL
D.2 | Prepare a note comparing technology between Smart Card vs Proximity Card Readers |  |  | 1999-09-06 | RL
D.3 | Issue Final Design Basis including Levels of Access |  |  | 1999-09-11 | CD/RL
D.4 | Prepare Requisition specs including General (KSS) Technical (RL) BoQ (HHP) Control room + commn. equipment Dwgs.(RL/HHP) Spares Terms & Conditions (AKC) |  |  | 1999-09-16 | RL/HHP
D.5 | Receive Final Quote |  | 1999-09-24 | 1999-09-27 | AKC
D.6 | Live Demo, Presentations and Techno-Commercial Discussions |  | 1999-09-27 | 1999-10-01 | Vendor / ALL
D.7 | LOI |  |  | 1999-10-07 | AKC
D.8 | Providing Data links at locations as required (if not already available) |  |  | 1999-11-18 | IT
D.9 | Electrical provisions at locations |  |  | 1999-11-18 | Electrical
D.10 | Expected date of Equipment availability for installation | 8 weeks |  | 1999-12-16 | Vendor
E. CCTV SYSTEM
E.1 | Finalise numbers and locations including location of control rooms (marking of dwgs.) |  |  | 1999-09-14 | CD/RL
E.2 | Issue Final Design Basis |  |  | 1999-09-16 | CD/RL
E.3 | Prepare Requisition specs including General (KSS) Technical (RL) BoQ (HHP) Control room + commn. equipment Dwgs. (RL/HHP) Spares Terms & Conditions (AKC) |  |  | 1999-09-16 | RL/HHP
E.4 | Receive Final Quote |  |  | 1999-09-27 | AKC
E.5 | Vendor discussions and negotiations |  | 1999-09-27 | 1999-10-01 | ALL
E.6 | LOI |  |  | 1999-10-07 | AKC
E.7 | Providing Data links at locations as required (if not already available) |  |  | 1999-11-18 | IT
E.8 | Electrical provisions at locations |  |  | 1999-11-18 | Electrical
E.9 | Civil works as per requirements at Camera locations |  |  | 1999-11-18 | Construction
E.10 | Expected date of Equipment availability for installation | 8 weeks |  | 1999-12-16 | Vendor
F. SECURITY CONTROL ROOM
F.1 | Prepare Design Basis |  | 1999-09-06 | 1999-09-09 | MPY
F.2 | Finalise Size and concept |  |  | 1999-09-09 | KSS/RL
F.3 | Provide input for SSM Office Fire Control Room First Aid |  |  | 1999-09-07 | JMM
F.4 | Prepare Final Sketch for the building |  |  | 1999-09-11 | KSS/RL
F.5 | Prepare Architectural GA |  |  | 1999-09-18 | SS
F.6 | Prepare Civil dwgs. |  |  | 1999-09-25 | FDC
F.7 | Order HVAC |  |  |  | AKC
F.8 | Construction |  |  | 1999-11-20 | Construction
F.9 | HVAC |  |  | 1999-12-04 | FDC
F.10 | Electrical wiring, fittings, etc. |  |  | 1999-12-04 | FDC
G. Miscellaneous Security Measures
G.1 | Identify locations of weak points of Perimeter Wall |  |  |  | CD/MPY
G.2 | Strengthen the wall including foundations wherever required |  |  |  | Construction
G.3 | Identify locations of waterways and pipe culverts |  |  |  | CD/MPY
G.4 | Waterways and pipe culverts to be blocked by removable grills |  |  |  | Construction